## Sheet1
# | Module | Page | Rekar Design Phase Comments | Status | issue Date | Developer Comments | Developer Status | Fixing Date
1 | General | All Pages | All images should be high quality |  | 2019-08-08
2 | General (AD's remove) | All Pages | No AD's content should be exist on all system pages, but the site should allow the system admin to add these AD's in the future once required |  | 2019-08-08
3 | Home Page Search | Home Page | Home Page should have the search feature as described in the SRS to be on the left side of the home page (as a vertical display container which includes on searchable fields in this container) |  | 2019-08-08
4 | All Modules | All Dynamic Pages | All pages which covered in the SRS as (Search, Car details, Listing, Renting, Registration, Admin Pages…etc) should consider the fields mentioned to be displayed/ filled/ interacted by the system users |  | 2019-08-08
5 | Home Page Design | Home Page | Home page navigation bar is not the same as Wix site |  | 2019-08-08
6 | General | All pages | Superuser should be able to change site colors/ images/ text contents/ resizing video section |  | 2019-08-08
7 | General | Missing Pages | Rent a car page/ List A Car/ Cars List Grid/ Car Details/ User Profile Pages (User Profile, Payment Methods List/ Payment Method inserting/ My Listed Cars/ My Rented Cars/ User Pay Page…all of these pages Have fields to be displayed and can be found in the SRS document |  | 2019-08-08
8 | User Registeration | Registeration Page | No verification on Email/ mobile/ Password Restrictions…Country/ City lookup not filled |  | 2019-08-08
9 | User Registeration | Registeration Page | Registeration button not functioning |  | 2019-08-08
10 | General | All Pages | Country control not designed as it’s a user friendly country selector, it should be more friendly in terms of look and having flag…etc as professional site |  | 2019-08-08
11 | General | Admin Missing Pages | Later on in the development phase, developer have to build Superuser "Admin Pages" like All listed cars/ User Complaints Receive page…all of these pages are described in the SRS |  | 2019-08-08
12 | General | Chat Bot | Chat bot is only allowed in page which is in the complaint page |  | 2019-08-08
13 | General | Static Content Pages | All static pages exist in Wix should be on the new site with user navigation allowed to see them |  | 2019-08-08